## Sheet1
Risks | Outcome | Likelihood (1-5) | Severity (1-5) | Rating (1-25) | Actions to Resolve
Running out of time | Project will be unfinished | 3 | 5 | 15 | Work and plan agile methodology efficiently
Personal injury | Project delayed or unfinished due to dev unable to work | 1 | 5 | 5 | Remain safe in accordance with health ansd safety whilst working
Hardware problems | Project delayed until hardware is fixed or suitable hardware replacement is found | 1 | 4 | 4 | Ensure backup hardware is available for use if necessary, ensure project is regularly commited to GitHub to avoid lost progress
Software problems | Project delayed until software issues are fixed | 2 | 2 | 4 | Ensure the team has support for software related issues and that all software and dependencies are documented and freely available for a clean install if necessary
Internet connection failing | Project delayed until connection is fixed | 3 | 1 | 3 | Find a separate conncection that is stable in case the primary network goes down, either through mobile tethering or at a secomd location.